## Frontend
HAEFA Frontend requirements
Project Status |  | Client's feedback list
Project Name |  | NIROG PLUS' (HAEFA)
Last Updated |  | 26/10/2023
Prepared by |  | Project Manager |  |  | Delivery Deadline: 01/11/2023
No. | Title | Description | Task Type | comment from Devs | Client's feedback | Status | QA Status
1 | Add new fields | · Spouse Name (if any) · Religion (dropdown) · Family Members · Father Name · Mother Name · Education(dropdown) · Head of Family(dropdown) Children (Age 0 to 1, Age 1 to 5, Age > 5) | New Task | API & patient registration done API list: Religion, Education, Head of Family | Hide these fields from frontend |  | PASSED
2 | Patient Registration | Would you please make if both addresses are same then the present address will be auto fill up with clicking a checkbox button. |  | No Backend Dependency |  |  | PASSED
3 | Patient's history in every station | Need all information (screenshot provided) and flagging system in patient history section. If any abnormality is showing in the patient test result the red/yellow flag will be shown depend on the test result value |  | API Development Done |  |  | HOLD
4 | Prescriotion | Details of HAEFA USA and HAEFA Bangladesh needs to be updated in the prescription footer. |  | No Backend Dependency |  |  | PASSED
5 | Prescription File Name | When we downloaded any prescription as a pdf then we can see it is downloading as Haefa.pdf. Would you please make it PRESCRIPTION_NUMBER.PDF |  | No Backend Dependency |  | done | PASSED
6 | Camera Rotation | Camera rotation functionality is not available. |  | Done |  | done | FAILED
7 | Error showing | Station 4A is showing an error when we are trying to insert few data. (Screenshot – 3) |  | changed status field, issue resolved |  | done | PASSED
8 | Next button not working ( Station 1) | After fill up all data into Station-1, the Save & Next button is not redirecting to next Station-2 |  | No Backend Dependency |  | done | PASSED
9 | Family member illness ( Station 4A) | We can not define which family member is in ill for specific patient (See screenshot-1) |  | need clarification
10 | Ttile change ( Station 4A) | Patient Mental Health should be title not a question.(4th question) |  | No Backend Dependency |  | done | PASSED
11 | Ttile change ( Station 4A) | Social History title is not relevant. (Title Should be: Do you take any of the followings?) |  | No Backend Dependency? |  | done | PASSED
12 | Duplicate advice (Station 4C) | One duplicated advice is showing here (dropdown) |  | Issue resolved |  | done | FAILED
13 | Ointment advice ( Station 4C) | Treatment Suggestion > Advice is not applicable for OINTMENTS. |  | Done? FE? |  | Done | HOLD
14 | Blank page | Sometimes, app interface is showing blank |  | ??IP change? Needs investigation
15 | Provisional Diagonostic (Station 4C) | We can search with any code/terms. But we can not define sub category of disease and we can not see disease code beside the Terms.Please see the attached video for more clarification (Attachment -4) |  | No Backend Dependency
16 | User Session | System will be automatically logged out if that specific user is inactive for last 30 mins. (Not necessary right now.) |  | No Backend Dependency
17 | TB Module |  |  | API List: |  | API provided

## Backend
HAEFA Backend requirements
| Project Status | Client's feedback list |  | Delivery Deadline: 10/01/2023
| Project Name | NIROG PLUS' (HAEFA)
| Last Updated | 25/10/2023
| Prepared By | Project Manager
No. | Title | Description | Task Type | comment from Devs | Client's feedback | Status
1 | User Tab | 1.1 Some field is not available in the user Tab which is available in previous version software.
1.2 Uploading of user's signature and Designation is not available in User registration.
2 | Patient Tab | 1. Add Patient button is not working 2. We can not select/wrtie Head of Family when we are trying to update a patients data. (Patient > Edit > Head of Family field)
Patient report is not properly implemented
3 | Health Center Tab | When we are try to insert Health center information, Some fields are not available which is available in previous version of NIROG. When we need to refer a patient to a nearest Health center then those information is needed for analysis. (See screenshot-5)
4 | Health Center Analysis Sec. | Please see the attachment here.(See screenshot-6)
5 | Referral Patient Section | This is needed if any HAEFA doctor refer a patient to other Health Center. Again we need to see how many referral patient in a specific duration in the report section. (See screenshot-7)
6 | Referral Data Section | We can not add/edit some reference data from backend. Those are given below: 1. Contraception Method, 2. Drug Form, 3. Drug Group, 4. Drug, 5. Head of Family 6. Lab investigation 7. Lab investigation group, 8. ill Family Member, 9. Provisional Diagnosis 10. Provisional Diagnosis Group 11. Disease Mapping to group.
7 | System Config. Section | 1. Auto Suggestion, 2. Auto Suggestion Group - NOT FOUND We can not add some reference data from backend. Those are given below: 1. Advice, 2. Duration, 3. Frequency 1. Advice, 2. Duration, 3. Frequency
8 | Data Sync | Would you please add a button to sync data from other database? Currently we have to click on a batch file to sync database.
9 | Database Backup | ?? NEED some Discussion.
10 | Barcode | 1. Sometime barcode is broken when we try to print it. Would you try to print just Health Center Name, District in header (remove Union and Upzilla) 2. Table action column button is not working in barcode generator menu. 3. Filtering to showing value 100, 50 is giving an error.
11 | Reports Section | 1. Every datatable first column name heading is not getting any space. 2. All dropdown menu is not fixed in every filter input area dropdown. It is moving when we scroll down/up. Please fix it for all the dropdown menu (See Screenshot 5) 3. In all prescription report, add new button is not working. Prescription footer is showing old HAEFA address.
12 | Analysis section
13 | Version Number | Would you please add Version Number and last updated date in the footer section?
14 | Speed Issue | Backend is very slow for use. We have now small amount of test data in the database but it takes too long for view or generate any report. There will be huge patient data in near future that time it will be very tough to generate/view some report and using the backend properly.
15 | Dashboard | Different type of charts is not properly implemented which we have provided earlier. (See the attachment-4)
16 | Backend Sidebar Menu Icon | Menu icon should be related one.
17 | File Upload List (Screenshot - 10)
18 | Charts | All the charts need to be developed as per attachment here.
19 | Employee | After insert RefEmployee, when we try to add him as a user, we can see there are Name, Employee Name. What does it mean by employee name? If we choose it, we can see in app frontend side, it is showing in the place of designation. (Screenshot – 12)
20 | Designation | We have a RefDesignation Menu to insert designation. When we try to insert a RefEmployee, we can see we have to write it instead of select from RefDesignation to this field as a dropdown selection.
21 | Naming Convention | Naming Convention: Currently, Reports file name is not related to that reports when we download it. Need to fix all reports name with the related one. Ex. Patients reports is downloaded as Haefa - Report- Total 299, Male 202, Female 97, Branch Name Balukhali FDMN Camp Camp 9 (Attachment -13)
22 | User
23 | Role
24 | Station
25 | Setting

## Summary
Summary of Test Requirements Traceability Matrix
Total No. of Requirements | New Requirements | Change Request | Requirements Approved | Requirements not Approved | Requirements Deferred | Requirements Reject

## RTM_Frontend_R
Test Requirements Traceability Matrix (TRTM)
Project Name | Nirog Plus (HAEFA) | [5 empty] | Create Date
Project ID | Project 05 | [5 empty] | Version | Nirog Plus Version: 2.0.0
Project Manager | Urmi Hira | [5 empty] | Client Name | Health and Education for All (HAEFA)
Project Type | NGO project | [5 empty] | QA Engineer | Rashed Zahan & Mustafa Tanim
Sl. no. |  | Req. ID | Req. Desc. | Source of Requirement | Scenario | TC ID | Test Desc. | Test Result | Defect ID | Defect Status
1 | Frontend | BR 1.0 | New fields add in registration page | New Requirement | Spouse Name (if any) | TC_SpouseName_001 | Placeholder of text field | HOLD
2 | Frontend |  |  |  |  | TC_SpouseName_002 | Title of text field | HOLD
3 | Frontend |  |  |  |  | TC_SpouseName_003 | Data insert into database | HOLD
4 | Frontend | BR 1.1 |  | New Requirement | Religion (dropdown) | TC_Religion_001 | Placeholder of text field | HOLD
5 | Frontend |  |  |  |  | TC_Religion_002 | Title of text field | HOLD
6 | Frontend |  |  |  |  | TC_Religion_003 | Dropdown functionality | HOLD
7 | Frontend |  |  |  |  | TC_Religion_004 | Data insert into database | HOLD
8 | Frontend | BR 1.2 |  | New Requirement | Family Members | TC_FamilyMem_001 | Placeholder of text field | HOLD
9 | Frontend |  |  |  |  | TC_FamilyMem_002 | Title of text field | HOLD
10 | Frontend |  |  |  |  | TC_FamilyMem_003 | Data insert into database | HOLD
11 | Frontend |  |  |  |  | TC_FamilyMem_004 | Numeric data input in the text field | HOLD
12 | Frontend | BR 1.3 |  | New Requirement | Father's Name | TC_FatherName_001 | Placeholder of text field | HOLD
13 | Frontend |  |  |  |  | TC_FatherName_002 | Title of text field | HOLD
14 | Frontend |  |  |  |  | TC_FatherName_003 | Data insert into database | HOLD
15 | Frontend | BR 1.4 |  | New Requirement | Mother's Name | TC_MotherName_001 | Placeholder of text field | HOLD
16 | Frontend |  |  |  |  | TC_MotherName_002 | Title of text field | HOLD
17 | Frontend |  |  |  |  | TC_MotherName_003 | Data insert into database | HOLD
18 | Frontend | BR 1.5 |  | New Requirement | Education(dropdown) | TC_Education_001 | Placeholder of text field | HOLD
19 | Frontend |  |  |  |  | TC_Education_002 | Title of text field | HOLD
20 | Frontend |  |  |  |  | TC_Education_003 | Dropdown functionality | FAILED | For "Others" > Should open text field & insert into database
21 | Frontend |  |  |  |  | TC_Education_004 | Data insert into database | HOLD
22 | Frontend | BR 1.6 |  | New Requirement | Head of Family (dropdown) | TC_FamilyHead_001 | Placeholder of text field | HOLD
23 | Frontend |  |  |  |  | TC_FamilyHead_002 | Title of text field | HOLD
24 | Frontend |  |  |  |  | TC_FamilyHead_003 | Dropdown functionality | HOLD
25 | Frontend |  |  |  |  | TC_FamilyHead_004 | Data insert into database | HOLD
26 | Frontend | BR 1.7 |  | New Requirement | Children (Age 0 to 1, Age 1 to 5, Age > 5) | TC_Children_001 | Placeholder of text field | HOLD
27 | Frontend |  |  |  |  | TC_Children_002 | Title of text field | HOLD
28 | Frontend |  |  |  |  | TC_Children_003 | Functionality | HOLD
29 | Frontend |  |  |  |  | TC_Children_004 | Data insert into database | HOLD
30 | Frontend | BR 2.0 | Present address and permanent address auto fill-up in registration page | Change Request | Auto Fillup Button | TC_AutoFillup_001 | Operational text message | PASS
31 | Frontend |  |  |  |  | TC_AutoFillup_002 | Button functionality | PASS
32 | Frontend |  |  |  |  | TC_AutoFillup_003 | Fillup present address > Click auto fillup button > Check permanent address | PASS
33 | Frontend |  |  |  |  | TC_AutoFillup_004 | Click auto fillup button > Fillup present address > Check permanent address | PASS
34 | Frontend |  |  |  |  | TC_AutoFillup_005 | Fillup present address > Click auto fillup button > Check permanent address > Edit/Update present address > Check permanent address | PASS
35 | Frontend | BR 3.0 | Red / Yellow Flag in patient history section | Change Request | Red / Yellow Flag | TC_Flag_001 | History showing properly | PASS
36 | Frontend |  |  |  |  | TC_Flag_002 | Red flag is showing perfectly | PASS
37 | Frontend |  |  |  |  | TC_Flag_003 | Yellow flag is showing perfectly | PASS
38 | Frontend | BR 4.0 | Address update on prescription | Change Request | Prescription | TC_Prescription_001 | Check prescription footer | PASS
39 | Frontend |  |  |  |  | TC_Prescription_002 | Check spelling of address | PASS
40 | Frontend | BR 5.0 | Download prescription | Change Request | Download file name | TC_FileName_001 | Check the file name when download | PASS
41 | Frontend |  |  |  |  | TC_FileName_002 | Check the file format | PASS
42 | Frontend | BR 6.0 | Front and rear camera rotation | Change Request | Camera Rotation | TC_CameraRotation_001 | Check camera rotation functionality | PASS
43 | Frontend | BR 7.0 | Station 4A is showing error to insert data. | Change Request | Error Showing | TC_ErrorShowing_001 | Check "Save & Next" button functionality | PASS
44 | Frontend | BR 8.0 | The "Save & Next" button is not redirected to Station-2 page | Change Request | Save & Next button | TC_SaveNext_001 | Check "Save & Next" button redirect to station 2 page | PASS
45 | Frontend | BR 9.0 | Which family member is ill | Change Request | Family member illness | TC_FamilyIllness_001 | Check which family member is ill for specific patient | PASS
46 | Frontend | BR 10.0 | Patient Mental Health should be title not a question | Change Request | Title Change | TC_TitleChange_001 | Check the title of patient mental health | PASS
47 | Frontend | BR 11.0 | Social History title is not relevant. (Title Should be: Do you take any of the followings?) | Change Request | Title Change | TC_SocialTitleChange_001 | Check the title of patient social history | PASS
48 | Frontend | BR 12.0 | One duplicated advice is showing under "Station 4C" | Change Request | Duplicate advice | TC_DuplicateAdvice_001 | Check dropdown value in advice section | PASS
49 | Frontend | BR 13.0 | Advice is not applicable for Ointment. | New Requirement | Ointment advice | TC_Ointment_Advice_001 | Check the functionality, how to use ointment | PASS
50 | Frontend | BR 14.0 | Sometimes, app interface is showing blank | Change Request | Blank Page | TC_BlankPage_001 | Check the app showing all information properly | Partially PASS
51 | Frontend | BR 15.0 | Sub category and disease code not found (Station 4C) | Change Request | Provisional Diagonostic | TC_Provisional Diagnosis_001 | Check the diseases code | PASS
52 | Frontend | [5 empty] | Check the sub category in this section | PASS
53 | Frontend | BR 16.0 | User session 30 mins | Change Request | User Session | TC_UserSession_001 | Check the user session in this application | PASS
54 | Frontend | BR 17.0 | TB module | New Requirements | TB Module | TC_TBModiul_001 | Check the dropdown functionality | PASS
55 | Frontend | BR 17.1 |  | New Requirements |  | TC_TBModiul_002 | Check the radio button functionality | PASS
56 | Frontend | BR 17.2 |  | New Requirements |  | TC_TBModiul_003 | Check the spelling mistake | PASS
57 | Frontend | BR 17.3 |  | New Requirements |  | TC_TBModiul_004 | Check the "Save & Next" button | PASS
58 | Frontend | BR 17.4 |  | New Requirements |  | TC_TBModiul_005 | Check the "History" button | PASS
59 | Frontend | BR 17.5 |  | New Requirements |  | TC_TBModiul_006 | Check "Save & Next" button redirect to station 4B page | PASS
60 | Frontend | BR 17.6 |  | New Requirements |  | TC_TBModiul_007 | Check "TB Status" page title | PASS
61 | Frontend | BR 17.7 |  | New Requirements |  | TC_TBModiul_008 | Check "TB Status" page url | PASS
62 | [5 empty] | TC_TBModiul_009 | Check the all checkbox | PASS
64 | Frontend |  | Patient age under one year | Change Request | Age Calculation | TC_AgeCalculation_001 | Patient age calculation under 1 year old | FAILED
64 | Frontend | BR 18.0 | Station-4C | Change Request | Treatment Suggestion | TC_TreatmentSuggestion_001 | Check the unit (dropdown) is only accept the integer number | FAILED

## RTMBackend_R
Test Requirements Traceability Matrix (TRTM)
Project Name |  | Nirog Plus (HAEFA) |  |  |  |  | Create Date
Project ID | [6 empty] | Version | Nirog Plus Version: 2.0.0
Project Manager |  | Urmi Hira |  |  |  |  | Client Name | Health and Education for All (HAEFA)
Project Type |  | Electronic Medical Record System Application |  |  |  |  | QA Engineer | Rashed Zahan & Mustafa Tanim
Sl. no. |  | Req. ID | Req. Desc. | Source of Requirement | Scenario | TC ID | Test Desc. | Test Result | Defect ID | Defect Status | Dev Com. Backend
1 | Backend | BR 1.0 | Some fields are not available in the user tab which is available in previous version software. | New Requirement | User Tab | TC_UserTab_001 | Check the fields in the sector | PASS
2 | Backend | BR 1.1 | Uploading of user's signature and Designation is not available in User registration. | Change Request | User Tab | TC_UserTab_001 | Check the user's signature and designation | Checked |  | 1. If needed, we have to mention mention image dimention, file format | PASS
3 | Backend | BR 2.0 | Add Patient button is not working | Change Request | Patient Tab | TC_PatientTab_001 | Check the button functionality | HOLD |  | Disable for user | PASS
4 | Backend | BR 2.1 | Patient report is not properly implemented | Change Request |  | TC_PatientTab_002 | Check the patient report functionality | PASS |  |  | PASS
5 | Backend | BR 2.2 | Patient data is not updating (Patient > Edit > Head of Family field) | Change Request |  | TC_PatientTab_003 | Check patient data update functionality | PASS |  |  | PASS
6 | Backend | BR 3.0 | Some fields are not available in Health center information | Change Request | Health Center Tab | TC_HealthCenter_001 | Check every fields are available | HOLD |  | Which kind of information are not availabe? these are not mentioned. | Phase 2.2
7 | Backend | BR 4.0 | Health Center Analysis Sec. | Change Request | Health Center Analysis | TC_HealthCenterAnalysis_001 |  | HOLD |  | Phase 2.2 | Phase 2.2
8 | Backend | BR 5.0 | Functionality testing | Change Request | Reference | TC_Refernce_001 | Check Auto suggestion functionality | Checked |  |  | PASS
9 | Backend | BR 5.1 | Functionality testing | Change Request |  | TC_Refernce_002 | Check Provisional Diagnosis functionality | Checked |  |  | PASS
10 | Backend |  |  | Change Request |  | TC_Refernce_003 | Check Lab Investigation functionality | Checked |  | Disease Mapping to group not found | PASS
11 | Backend | BR 5.2 | Functionality testing | Change Request |  | TC_Refernce_004 | Check Vaccine Dose functionality | Checked |  |  | PASS
12 | Backend |  | Functionality testing | Change Request |  | TC_Refernce_005 | Check Drug functionality | Checked |  |  | PASS
13 | Backend | BR 5.3 | Functionality testing | Change Request |  | TC_Refernce_006 | Check Address type functionality |  |  |  | PASS
14 | Backend |  | Functionality testing | Change Request |  | TC_Refernce_007 | Check Drug Form functionality | Checked |  |  | PASS
15 | Backend | BR 5.4 | Functionality testing | Change Request |  | TC_Refernce_008 | Check Question Type functionality | Checked |  |  | PASS
16 | Backend |  | Functionality testing | Change Request |  | TC_Refernce_009 | Check Auto Suggestion Group functionality | Checked |  |  | PASS
17 | Backend | BR 5.5 | Functionality testing | Change Request |  | TC_Refernce_010 | Check Biopsy Result functionality | Checked |  |  | PASS
18 | Backend |  | Functionality testing | Change Request |  | TC_Refernce_011 | Check Social Behavior functionality | Checked |  |  | PASS
19 | Backend | BR 5.6 | Functionality testing | Change Request |  | TC_Refernce_012 | Check Referral functionality | Checked |  |  | PASS
20 | Backend |  | Functionality testing | Change Request |  | TC_Refernce_013 | Check Religion functionality | Checked |  |  | PASS
21 | Backend | BR 5.7 | Functionality testing | Change Request |  | TC_Refernce_014 | Check Ill Family member functionality | Checked |  |  | PASS
22 | Backend |  | Functionality testing | Change Request |  | TC_Refernce_015 | Check Question functionality | PASS |  |  | PASS
23 | Backend | BR 5.8 | Functionality testing | Change Request |  | TC_Refernce_016 | Check Most product Usage Time functionality | Checked |  |  | PASS
24 | Backend |  | Functionality testing | Change Request |  | TC_Refernce_017 | Check Contraception Method functionality | Checked |  |  | PASS
25 | Backend | BR 5.5 | Functionality testing | Change Request |  | TC_Refernce_018 | Check Cancer Treatment functionality | Checked |  |  | PASS
26 | Backend |  | Functionality testing | Change Request |  | TC_Refernce_019 | Check Menstruation Product functionality | Checked |  |  | PASS
27 | Backend | BR 5.4 | Functionality testing | Change Request |  | TC_Refernce_020 | Check Instruction functionality | Checked |  |  | PASS
28 | Backend |  | Functionality testing | Change Request |  | TC_Refernce_021 | Check Provisional Diagnosis Group functionality | Checked |  |  | PASS
29 | Backend | BR 5.5 | Functionality testing | Change Request |  | TC_Refernce_022 | Check Marital Status functionality | Checked |  |  | PASS
30 | Backend |  | Functionality testing | Change Request |  | TC_Refernce_023 | Check Refillness functionality | Checked |  |  | PASS
31 | Backend | BR 5.6 | Functionality testing | Change Request |  | TC_Refernce_024 | Check Education functionality | Checked |  |  | PASS
32 | Backend |  | Functionality testing | Change Request |  | TC_Refernce_025 | Check Lab Investigation Group functionality | Checked |  |  | PASS
33 | Backend |  | Functionality testing | Change Request |  | TC_Refernce_026 | Check Frequency functionality | Checked |  |  | PASS
34 | Backend |  | Functionality testing | Change Request |  | TC_Refernce_027 | Check Department functionality | Checked |  |  | PASS
35 | Backend |  | Functionality testing | Change Request |  | TC_Refernce_028 | Check Gender functionality | Checked |  |  | PASS
36 | Backend |  | Functionality testing | Change Request |  | TC_Refernce_029 | Check Duration functionality | Checked |  |  | PASS
37 | Backend |  | Functionality testing | Change Request |  | TC_Refernce_030 | Check Drug Group functionality | Checked |  |  | PASS
38 | Backend |  | Functionality testing | Change Request |  | TC_Refernce_031 | Check Designation functionality | Checked |  |  | PASS
39 | Backend |  | Functionality testing | Change Request |  | TC_Refernce_032 | Check Chief Complaints functionality | Checked |  |  | PASS
40 | Backend |  | Functionality testing | Change Request |  | TC_Refernce_033 | Check Disease Group functionality | Checked |  |  | PASS
41 | Backend |  | Functionality testing | Change Request |  | TC_Refernce_034 | Check Blood Group functionality | Checked |  |  | PASS
42 | Backend |  | Functionality testing | Change Request |  | TC_Refernce_035 | Check Upazilla functionality | Checked |  |  | PASS
43 | Backend |  | Functionality testing | Change Request |  | TC_Refernce_036 | Check Health Center functionality | Checked |  |  | PASS
44 | Backend |  | Functionality testing | Change Request |  | TC_Refernce_037 | Check Employee functionality | Checked |  |  | PASS
45 | Backend |  | Functionality testing | Change Request |  | TC_Refernce_038 | Check Union functionality | Checked |  |  | PASS
46 | Backend |  | Functionality testing | Change Request |  | TC_Refernce_039 | Check Vaccine Child functionality | Checked |  |  | PASS
47 | Backend |  | Functionality testing | Change Request |  | TC_Refernce_040 | Check Vaccine Adult functionality | Checked |  |  | PASS
48 | Backend | BR 7.0 | Can not add some reference data from backend | Change Request | System Config. Section | TC_SystemConfig_001 | 1. Auto Suggestion, 2. Auto Suggestion Group - NOT FOUND. We can not add some reference data from backend. Those are given below: 1. Advice, 2. Duration, 3. Frequency | Checked |  |  | PASS
49 | Backend | BR 8.0 | Add a button to sync data from other database | Change Request | Data Sync | TC_DataSync_001 | Check the data sync button functionality | HOLD |  |  | To be discuess Phase 2.2
50 | Backend | BR 9.0 | Need a software for database backup | Change Request | Database Backup | TC_DatabaseBackup_001 | Check database auto-backup | HOLD |  |  | To be discuess Phase 2.2
51 | Backend | BR 10.0 | Sometime barcode is broken | Change Request | Barcode | TC_Barcode_001 | Check the barcode is broken or not | Checked |  |  | PASS
52 | Backend | BR 10.1 | Print just Health Center Name, District in header (remove Union and Upzilla) | New Requirement |  | TC_Barcode_002 | Check barcode design and information | Checked |  |  | PASS
53 | Backend |  | Table action column button is not working in barcode generator menu. | Change Request |  | TC_Barcode_003 | Check action column button | HOLD |  | No need | PASS
54 | Backend |  | Filtering to showing value 100, 50 is giving an error. | Change Request |  | TC_Barcode_004 | Check the data table length functionality | Checked |  |  | PASS
55 | Backend | BR 11.0 | Report generate | Change Request | Reports Section | TC_ReportSection_001 | Check "Age wise provisional Diagnosis" reports | Checked | DF_001 |  | PASS
56 | Backend |  |  | Change Request |  | TC_ReportSection_002 | Check "Provisional Diagnosis Patient Count Age Wise" reports | Checked | DF_002 |  | PASS
57 | Backend |  |  | Change Request |  | TC_ReportSection_003 | Check "Datewise Provisional DX" reports | Checked | DF_003 |  | PASS
58 | Backend |  |  | New Requirement |  | TC_ReportSection_004 | Check "Blood Pressure" reports | Checked | DF_006 |  | PASS
59 | Backend |  |  | New Requirement |  | TC_ReportSection_005 | Check "Chart of Diseases" reports | Checked | DF_005 |  | PASS
60 | Backend |  |  | New Requirement |  | TC_ReportSection_006 | Check "Custom Report" section | Checked |  |  | PASS
61 | Backend |  |  | New Requirement |  | TC_ReportSection_007 | Check "All Disease" report | Checked | DF_011 |  | PASS
62 | Backend |  |  | New Requirement |  | TC_ReportSection_008 | Check "Disease rate" reports | Checked | DF_007 |  | PASS
63 | Backend |  |  | New Requirement |  | TC_ReportSection_009 | Check "Diabetes Mellitus" reports | Checked |  |  | PASS
64 | Backend |  |  | Change Request |  | TC_ReportSection_010 | Check "FollowUpDate" reports | Checked | DF_004 |  | PASS
65 | Backend |  |  | New Requirement |  | TC_ReportSection_011 | Check "Full Data Export" report | Checked |  |  | In Progress
66 | Backend |  |  | New Requirement |  | TC_ReportSection_012 | Check "Full Data Dump" report | Checked |  |  | PASS
67 | Backend |  |  | Change Request |  | TC_ReportSection_013 | Check "Treatment Suggestions" reports | Checked | DF_009 |  | PASS
68 | Backend |  |  | New Requirement |  | TC_ReportSection_014 | Check "All Prescriptions" report | Checked |  |  | PASS
69 | Backend |  |  | New Requirement |  | TC_ReportSection_015 | Check "Patients" report | HOLD |  | Not found | No need
70 | Backend |  |  | New Requirement |  | TC_ReportSection_016 | Check "Referred Case" report | HOLD |  | Not found | To be discuess Phase 2.2
71 | Backend |  |  | New Requirement |  | TC_ReportSection_017 | Check "Patient Count Age" report | Checked |  | Ascending and descending button missing but still working. | No need
72 | Backend |  |  | New Requirement |  | TC_ReportSection_018 | Check "District Wise Patient" report | HOLD |  | Not found | No need
73 | Backend | BR 11.1 | Every datatable first column name heading is not getting any space. | Change Request |  | TC_ReportSection_019 | Check data table first column name | PASS |  |  | PASS
74 | Backend | BR 11.2 | All dropdown menu is not fixed in every filter input area dropdown. It is moving when we scroll down/up. Please fix it for all the dropdown menu | Change Request |  | TC_ReportSection_020 | Check the dropdown functionality | Checked |  |  | PASS
75 | Backend | BR 11.3 | In all prescription report, add new button is not working | Change Request |  | TC_ReportSection_021 | Check add new button | HOLD |  | No need | PASS
76 | Backend | BR 11.4 | Prescription footer is showing old HAEFA address. | Change Request |  | TC_ReportSection_022 | Check prescription footer address | Checked |  |  | PASS
77 | Backend | BR 12.0 | Analysis report section | New Requirement | Analysis section | TC_AnalysisSection_001 | Check every analysis report section | HOLD |  | Phase 2.2 | To be discuess Phase 2.2
78 | Backend | BR 13.0 | Add Version Number and last updated date in the footer section | New Requirement | Version Number | TC_VersionNumber_001 | Check the version number and updated date | Checked |  |  | PASS
79 | Backend | BR 14.0 | Backend is very slow | Change Request | Speed Issue | TC_SpeedIssue_001 | Site load test | HOLD |  | Server issue (Not suitable for performance testing) | No comments
80 | Backend | BR 14.1 |  |  |  | TC_SpeedIssue_002 | Report generate speed test | HOLD |  | Server issue (Not suitable for performance testing) | No comments
81 | Backend | BR 15.0 | 0 | New Requirement | Dashboard | TC_Dashboard_001 | Check the chart from dashboard | Checked |  |  | PASS
82 | Backend | BR 15.1 |  |  |  | TC_Dashboard_002 | Check the graph from dashboard | PASS |  | Not found any graph | PASS
83 | Backend | BR 16.0 | Menu icon should be related one. | Change Request | Backend Side Menu | TC_BackendSideMenu_001 | Check the side menu UI/UX | FAILED |  | Not responsive | Admin Panel only Support Laptop and Desktop Screen
84 | Backend | BR 17.0 | File Upload List | New Requirement | File Upload List | TC_FileUpload_001 | Check the file upload function | Checked |  | Need to mention file size and file format. | Not Clear
85 | Backend | BR 18.0 | All the charts need to be developed as per attachment here. | New Requirement | Charts | TC_Charts_001 | Check the charts on dashboard | Checked |  |  | PASS
86 | Backend | BR 19.0 | What does it mean by employee name | Change Request | Employee | TC_Employee_001 | Check the employee add section | Checked |  |  | PASS
87 | Backend |  |  |  |  | TC_Employee_002 | Check the user section for employee | Checked |  |  | PASS
88 | Backend | BR 20.0 | Designation dropdown under the employee section | Change Request | Designation | TC_Designation_001 | Check to create a new designation | Checked |  |  | PASS
89 | Backend |  |  | Change Request |  | TC_Designation_002 | Check designation dropdown under the employee field | Checked |  |  | PASS
90 | Backend | BR 21.0 | Report download file name | Change Request | Naming Convention | TC_NamingConvention_001 | Check report download file name | Checked |  |  | PASS
91 | Backend | BR 22.0 | Access Control > User: Functionality/UI | Change Request | User | TC_User_001 | Check new user 'add new' button functionality | Checked | DF_12 | Station name should be mentioned by the required field. | PASS
92 | Backend | BR 22.1 |  | Change Request |  | TC_User_002 | Check user page breadcrumb | Checked |  |  | PASS
93 | Backend | BR 22.2 |  | Change Request |  | TC_User_003 | Check user page title | Checked |  |  | PASS
94 | Backend | BR 22.3 |  | Change Request |  | TC_User_004 | Check user page url | Checked |  |  | PASS
95 | Backend | BR 22.4 |  | Change Request |  | TC_User_005 | Check user page "search" button funtionality | Checked |  |  | PASS
96 | Backend | BR 22.5 |  | Change Request |  | TC_User_006 | Check user page "reset" button funtionality | Checked |  |  | PASS
97 | Backend | BR 22.6 |  | Change Request |  | TC_User_007 | Check user page "action" button funtionality | Checked |  |  | PASS
98 | Backend | BR 22.7 |  | Change Request |  | TC_User_008 | Check user page "status" button funtionality | Checked |  |  | PASS
99 | Backend | BR 22.8 |  | Change Request |  | TC_User_009 | Check user page dropdown | Checked |  |  | PASS
100 | Backend | BR 22.9 |  | Change Request |  | TC_User_010 | check next page button functionality | Checked |  |  | PASS
101 | Backend | BR 22.10 |  | Change Request |  | TC_User_011 | check previous page button functionality | Checked |  |  | PASS
102 | Backend | BR 22.11 |  | Change Request |  | TC_User_012 | Check the placeholder of textfield | Checked |  |  | PASS
103 | Backend | BR 22.12 |  | Change Request |  | TC_User_013 | Check the "data table length" functionality | Checked |  |  | PASS
104 | Backend | BR 23.0 | Access Control > Role: Functionality/UI | Change Request | Role | TC_Role_001 | Check new user 'add new' button functionality | Checked |  |  | PASS
105 | Backend | BR 23.1 |  | Change Request |  | TC_Role_002 | Check role page breadcrumb | Checked |  |  | PASS
106 | Backend | BR 23.2 |  | Change Request |  | TC_Role_003 | Check role page title | Checked |  |  | PASS
107 | Backend | BR 23.3 |  | Change Request |  | TC_Role_004 | Check role page url | Checked |  |  | PASS
108 | Backend | BR 23.4 |  | Change Request |  | TC_Role_005 | Check role page "search" button funtionality | Checked |  |  | PASS
109 | Backend | BR 23.5 |  | Change Request |  | TC_Role_006 | Check role page "action" button funtionality | Checked |  |  | PASS
110 | Backend | BR 23.6 |  | Change Request |  | TC_Role_007 |  |  |  | Pending | PASS
111 | Backend | BR 23.7 |  | Change Request |  | TC_Role_008 | Check role page dropdown | Checked |  |  | PASS
112 | Backend | BR 23.8 |  | Change Request |  | TC_Role_009 | check next page button functionality | Checked |  |  | PASS
113 | Backend | BR 23.9 |  | Change Request |  | TC_Role_010 | check previous page button functionality | Checked |  |  | PASS
114 | Backend | BR 23.10 |  | Change Request |  | TC_Role_011 | Check the placeholder of textfield | Checked |  |  | PASS
115 | Backend | BR 23.11 |  | Change Request |  | TC_Role_012 | Check the "data table length" functionality | Checked |  |  | PASS
116 | Backend | BR 23.12 |  | Change Request |  | TC_Role_013 | Check the "checkbox" functionality | Checked |  |  | PASS

## Revision_History
S. No | Date | Version No | Prepared By | Approved By | Remarks
1
2
3
4
5
6
7
8
9
10

## BackendDefectStatus
HAEFA Backend Defect Report
Reference: Client report format
Defect ID | Def. Description | Dev. Comment | Dev Status | Test Status | Final Status
DF_001 | 1. Getting data alignment, not in center 2. Download file name is not okay 3. Column name overlapping 4. Reset button is not working properly 5. Page title is not relevant | 1. No change needed now (PM) 2. Updated but not as per required file name. 3. Now working properly 4. Reset button is functional as per requirement 5. No change needed now (PM)
DF_002 | 1. Column Mismatch "EmployeeID > RegistrationID 2. Required age value is "Float" | 1. Okay as per requirements 2. Okay as per requirements
DF_003 | 1. Page heading is not related to menu name 2. Default date is not working 3. "Export to Excel" button can download Empty file. 4. Data has been removed when ckicked on "Export & Excel" button 5. Reset button is not working properly | 1. Now Okay 2. Working as per requirement 3. No change needed now (PM) 4. Working as per requirement 5. Working as per requirement
DF_004 | 1. Getting data alignment are not in center 2. Reset button is not working properly 3. Default date is not working 4. Duplicate data showing in report / Frontend is receiving multiple followup date 5. Reset button is not working properly
DF_005 | 1. Tooltip is missing to "Reset" & "Search" button 2. "Reset" & "Search" button position 3. "Patient" button not understandable | 1. Not Fixed 2. Fixed 3.
DF_006 | 1. Patient dropdown field has been broken. 2. Reset button not working properly 3. | 1. Fixed 2. Fixed
DF_007 | 1."Reset" button is missing. Need to clear concept
DF_008
DF_009 | 1. Page heading should be changed 2. "Reset" button is not working properly 3. "Export to Excel" button can download Empty file.
DF_010
DF_011 | 1. Page heading is not relevant 2. Refresh button is missing 3. Date range filter option has been session out after clinking on search button. To understand which date range we pick, date range filter should be fixed as we select 4. Disease search not working properly | 1. Fixed 2. Fixed 3.
DF_012 | 1 2

## FrontendDefectStatus
HAEFA Frontend Defect Report
Reference: Client report format
Defect ID | Def. Description | Dev. Comment | Dev Status | Test Status | Final Status
DF_001
DF_002
DF_003
DF_004
DF_005
DF_006
DF_007
DF_008
DF_009
DF_010
DF_011
DF_012

## DecisionTable
Decision Table | *** | *** | ** | * | **
Conditions | Rule 1 | Rule 2 | Rule 3 | Rule 4 | Rule 5 | Result
Age wise provisional Diagnosis | T | F | T | T | T | PASS
Provisional Diagnosis | T | T | - | - | - | PASS
Datewise Provisional DX | T | T | T | T | T | PASS